## Table 1
NORTHERN CALIFORNIA POWER AGENCY
CALENDAR YEAR 2018
PLANNED MAINTENANCE OUTAGE SCHEDULE
Facility | Jan. | Feb. | Mar. | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec.
Collierville Unit 1 | Oct.: 6-7 and 8-19
Collierville Unit 2 | Oct.: 6-7 and 10/22-11/21; Nov.: 10/22-11/21
Spicer Unit 1 | Sept.: 10-13
Spicer Unit 2 | Sept.: 17-20
Spicer Unit 3 | Sept.: 24-27
CT1 Alameda Project | Mar.: 12-23
CT1 Lodi Project | May: 7-18
CT2 STIG Project | April: 15-22
Lodi Energy Center | April: 2-22
Geothermal Plant 1 Unit 1 | April: 2-6
Geothermal Plant 1 Unit 2 | April: 2-6
Geothermal Plant 2 Unit 4 | April: 16-20
Proposed 7-5-2017